## TEAM
Team
João Félix (Product Owner)
Luís Lamy (Scrum Master)
Guilherme Santana (Quality Controller)
Yaroslav Hayduk (Team Member)
Bernardo Carvalho (Team Member)

## GANTT CHART
Gantt Chart
| Project Start | 2025-03-31 |  |  | columns used to create the chart
CATEGORY | TASK | START | END | COLOR | Start | Blue | Red | Green | Brown | Orange | Purple | Working Days
Planning | Define Team Roles and Responsibilities #1 | 2025-04-08 | 2025-04-08 | Blue | 2025-04-08 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| Gantt Chart and Task Dependencies #2 | 2025-04-08 | 2025-04-08 | Blue | 2025-04-08 | 1 | 0 | 0 | 0 | 0 | 0 | 1
Documentation | Generate Sprint 1 Burndown Chart #3 | 2025-04-09 | 2025-04-10 | Blue | 2025-04-09 | 2 | 0 | 0 | 0 | 0 | 0 | 2
| SysML diagram for 15 FR. #4 | 2025-04-10 | 2025-04-15 | Blue | 2025-04-10 | 6 | 0 | 0 | 0 | 0 | 0 | 6
| Model Main Business Process and Features (BPMN) #5 | 2025-04-12 | 2025-04-16 | Red | 2025-04-12 | 0 | 5 | 0 | 0 | 0 | 0 | 5
Back End | Implement Back-End Logic for Basic Features #8 | 2025-04-15 | 2025-04-22 | Red | 2025-04-15 | 0 | 8 | 0 | 0 | 0 | 0 | 8
Front End | Design Front-End UI #6 | 2025-04-16 | 2025-04-20 | Red | 2025-04-16 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Implement Front-End #7 | 2025-04-18 | 2025-04-23 | Red | 2025-04-18 | 0 | 6 | 0 | 0 | 0 | 0 | 6
Quality | Quality Check and Testing #9 | 2025-04-22 | 2025-04-27 | Green | 2025-04-22 | 0 | 0 | 6 | 0 | 0 | 0 | 6
Insert new rows above this one
| MILESTONE LABEL | DATE | Margin Bottom | Margin Top
| Start Coding | 2025-04-17 | 50% | 95%
| 1st Delivery | 2025-04-27 | 25% | 95%
Formulas:
Start = IF(ISBLANK([START]),0,[START])

## BURNDOWN CHART
Burndown Chart
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
CATEGORY | TASK | START | END | ESTIMATE (Hours) | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | REMAINING WORK
Planning | Define Team Roles and Responsibilities #1 | 2025-04-08 | 2025-04-08 | 0.5 | 2025-04-08: 0.5 | 0
| Gantt Chart and Task Dependencies #2 | 2025-04-08 | 2025-04-08 | 3 | 2025-04-08: 3 | 0
Documentation | Generate Sprint 1 Burndown Chart #3 | 2025-04-09 | 2025-04-10 | 1 | [20 empty] | 0 | bar: 2025-04-08
| SysML diagram for 15 FR. #4 | 2025-04-10 | 2025-04-15 | 35 | 2025-04-13: 1; 2025-04-14: 5.5; 2025-04-15: 3.5; 2025-04-16: 1.25; 2025-04-17: 1.5; 2025-04-18: 4; 2025-04-21: 5.5 | 12.75
| Model Main Business Process and Features (BPMN) #5 | 2025-04-12 | 2025-04-16 | 30 | 2025-04-13: 3; 2025-04-15: 4; 2025-04-17: 2; 2025-04-18: 7.5; 2025-04-19: 1.5; 2025-04-20: 2 | 10
Back End | Implement Back-End Logic for Basic Features #8 | 2025-04-15 | 2025-04-22 | 50 | [20 empty] | 50
Front End | Design Front-End UI #6 | 2025-04-16 | 2025-04-20 | 1 | [20 empty] | 0 | bar: 2025-04-17
| Implement Front-End #7 | 2025-04-18 | 2025-04-23 | 35 | 2025-04-21: 1.5 | 33.5
Quality | Quality Check and Testing #9 | 2025-04-22 | 2025-04-27 | 35 | [20 empty] | 35
|  |  | Total | 190.5 | 4.5 | 0 | 0 | 0 | 0 | 4 | 5.5 | 7.5 | 1.25 | 4.5 | 11.5 | 1.5 | 2 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 141.25
| Work divided by the whole team |  | Remaining | 190.5 | 186 | 186 | 186 | 186 | 186 | 182 | 176.5 | 169 | 167.75 | 163.25 | 151.75 | 150.25 | 148.25 | 141.25 | 141.25 | 141.25 | 141.25 | 141.25 | 141.25 | 141.25
|  |  | Ideal | 190.5 | 180.975 | 171.45 | 161.925 | 152.4 | 142.875 | 133.35 | 123.825 | 114.3 | 104.775 | 95.25 | 85.725 | 76.2 | 66.675 | 57.15 | 47.625 | 38.1 | 28.575 | 19.05 | 9.525 | 0
|  |  | TEAM MEMBERS | ESTIMATE (Hours) | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | REMAINING WORK
|  |  | Bernardo Carvalho | 30.1 | 2025-04-08: 0.1; 2025-04-14: 2.5; 2025-04-15: 2.5; 2025-04-18: 4.5 | 20.5
|  |  | Guilherme Santana | 68.1 | 2025-04-08: 3.1; 2025-04-19: 0.5; 2025-04-20: 2; 2025-04-21: 5.5 | 57
|  |  | João Félix | 30.1 | 2025-04-08: 0.1; 2025-04-13: 3; 2025-04-15: 2; 2025-04-16: 1; 2025-04-18: 4; 2025-04-21: 1.5 | 18.5
|  |  | Luís Lamy | 32.1 | 2025-04-08: 1.1; 2025-04-15: 1; 2025-04-16: 0.25; 2025-04-17: 2.5; 2025-04-18: 1 | 26.25
|  |  | Yaroslav Hayduk | 30.1 | 2025-04-08: 0.1; 2025-04-13: 1; 2025-04-14: 3; 2025-04-15: 2; 2025-04-17: 2; 2025-04-18: 2; 2025-04-19: 1 | 19
|  |  | Total | 190.5 | 4.5 | 0 | 0 | 0 | 0 | 4 | 5.5 | 7.5 | 1.25 | 4.5 | 11.5 | 1.5 | 2 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 141.25
|  |  | Remaining | 190.5 | 186 | 186 | 186 | 186 | 186 | 182 | 176.5 | 169 | 167.75 | 163.25 | 151.75 | 150.25 | 148.25 | 141.25 | 141.25 | 141.25 | 141.25 | 141.25 | 141.25 | 141.25
|  |  | Ideal | 190.5 | 180.975 | 171.45 | 161.925 | 152.4 | 142.875 | 133.35 | 123.825 | 114.3 | 104.775 | 95.25 | 85.725 | 76.2 | 66.675 | 57.15 | 47.625 | 38.1 | 28.575 | 19.05 | 9.525 | 0
Tasks Assigned
All
Define Team Roles and Responsibilities #1 (0.5 hours)
João Félix (Product Owner)
SysML diagram for 3 FR #4 (5 hours)
Model Main Business Process (BPMN) #5 (6 hours)
Implement Back-End Logic for Basic Features #8 (10 hours)
Implement Front-End #7 (7 hours)
Luís Lamy (Scrum Master)
Generate Sprint 1 Burndown Chart #3 (1 hour)
SysML diagram for 3 FR #4 (5 hours)
Model Main Business Process (BPMN) #5 (6 hours)
Implement Back-End Logic for Basic Features #8 (10 hours)
Design Front-End UI #6 (30 hours)
Implement Front-End #7 (7 hours)
Guilherme Santana (Quality Controller)
Gantt Chart and Task Dependencies #2 (3 hours)
SysML diagram for 3 FR #4 (5 hours)
Model Main Business Process (BPMN) #5 (6 hours)
Implement Back-End Logic for Basic Features #8 (10 hours)
Implement Front-End #7 (7 hours)
Quality Check and Testing #9 (35 hours)
Yaroslav Hayduk (Team Member)
SysML diagram for 3 FR #4 (5 hours)
Model Main Business Process (BPMN) #5 (6 hours)
Implement Back-End Logic for Basic Features #8 (10 hours)
Implement Front-End #7 (7 hours)
Bernardo Carvalho (Team Member)
SysML diagram for 3 FR #4 (5 hours)
Model Main Business Process (BPMN) #5 (6 hours)
Implement Back-End Logic for Basic Features #8 (10 hours)
Implement Front-End #7 (7 hours)