## TEAM
Team
João Félix (Product Owner)
Luís Lamy (Scrum Master)
Guilherme Santana (Quality Controller)
Yaroslav Hayduk (Team Member)
Bernardo Carvalho (Team Member)

## GANTT CHART
Gantt Chart
| Project Start | 2025-03-31 |  |  | columns used to create the chart
CATEGORY | TASK | START | END | COLOR | Start | Blue | Red | Green | Brown | Orange | Purple | Working Days
Planning | Define Team Roles and Responsibilities #1 | 2025-04-08 | 2025-04-08 | Blue | 2025-04-08 | 1 | 0 | 0 | 0 | 0 | 0 | 1
| Gantt Chart and Task Dependencies #2 | 2025-04-08 | 2025-04-08 | Blue | 2025-04-08 | 1 | 0 | 0 | 0 | 0 | 0 | 1
Documentation | Generate Sprint 1 Burndown Chart #3 | 2025-04-09 | 2025-04-10 | Blue | 2025-04-09 | 2 | 0 | 0 | 0 | 0 | 0 | 2
| SysML diagram for 15 FR. #4 | 2025-04-10 | 2025-04-15 | Blue | 2025-04-10 | 6 | 0 | 0 | 0 | 0 | 0 | 6
| Model Main Business Process and Features (BPMN) #5 | 2025-04-12 | 2025-04-16 | Red | 2025-04-12 | 0 | 5 | 0 | 0 | 0 | 0 | 5
Back End | Implement Back-End Logic for Basic Features #8 | 2025-04-15 | 2025-04-22 | Red | 2025-04-15 | 0 | 8 | 0 | 0 | 0 | 0 | 8
Front End | Design Front-End UI #6 | 2025-04-16 | 2025-04-20 | Red | 2025-04-16 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Implement Front-End #7 | 2025-04-18 | 2025-04-23 | Red | 2025-04-18 | 0 | 6 | 0 | 0 | 0 | 0 | 6
Quality | Quality Check and Testing #9 | 2025-04-22 | 2025-04-27 | Green | 2025-04-22 | 0 | 0 | 6 | 0 | 0 | 0 | 6
Insert new rows above this one
| MILESTONE LABEL | DATE | Margin Bottom | Margin Top
| Start Coding | 2025-04-17 | 50% | 95%
| 1st Delivery | 2025-04-27 | 25% | 95%
Formulas:
Start = IF(ISBLANK([START]),0,[START])

## BURNDOWN CHART
Burndown Chart
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
CATEGORY | TASK | START | END | ESTIMATE (Hours) | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | REMAINING WORK
Planning | Define Team Roles and Responsibilities #1 | 2025-04-08 | 2025-04-08 | 0.5 | 2025-04-08: 0.5 | 0
| Gantt Chart and Task Dependencies #2 | 2025-04-08 | 2025-04-08 | 3 | 2025-04-08: 3 | 0
Documentation | Generate Sprint 1 Burndown Chart #3 | 2025-04-09 | 2025-04-10 | 1 | [20 empty] | 0 | bar: 2025-04-08
| SysML diagram for 15 FR. #4 | 2025-04-10 | 2025-04-15 | 24.25 | 2025-04-13: 1; 2025-04-14: 5.5; 2025-04-15: 3.5; 2025-04-16: 1.25; 2025-04-17: 1.5; 2025-04-18: 4; 2025-04-21: 5.5; 2025-04-24: 1; 2025-04-26: 1 | 0
| Model Main Business Process and Features (BPMN) #5 | 2025-04-12 | 2025-04-16 | 25.5 | 2025-04-13: 3; 2025-04-15: 4; 2025-04-17: 2; 2025-04-18: 7.5; 2025-04-19: 1.5; 2025-04-20: 2; 2025-04-23: 2; 2025-04-24: 1; 2025-04-26: 2; 2025-04-27: 0.5 | 0
Back End | Implement Back-End Logic for Basic Features #8 | 2025-04-15 | 2025-04-22 | 20 | 2025-04-22: 4; 2025-04-23: 4; 2025-04-24: 2; 2025-04-25: 6; 2025-04-26: 4 | 0
Front End | Design Front-End UI #6 | 2025-04-16 | 2025-04-20 | 7.5 | 2025-04-17: 1; 2025-04-23: 2; 2025-04-24: 2; 2025-04-25: 2.5 | 0
| Implement Front-End and Back-End #7 | 2025-04-18 | 2025-04-23 | 5 | 2025-04-21: 1.5; 2025-04-22: 1; 2025-04-23: 1; 2025-04-24: 0.5; 2025-04-25: 1 | 0
Quality | Quality Check and Testing #9 | 2025-04-22 | 2025-04-27 | 11.5 | 2025-04-22: 2; 2025-04-24: 0.5; 2025-04-25: 1; 2025-04-26: 3; 2025-04-27: 5 | 0
Report | Write a report on the project | 2025-04-23 | 2025-04-27 | 8 | 2025-04-26: 1; 2025-04-27: 7 | 0
|  |  | Total | 106.25 | 4.5 | 0 | 0 | 0 | 0 | 4 | 5.5 | 7.5 | 1.25 | 4.5 | 11.5 | 1.5 | 2 | 7 | 7 | 9 | 7 | 10.5 | 11 | 12.5 | 0
|  |  | Remaining | 106.25 | 101.75 | 101.75 | 101.75 | 101.75 | 101.75 | 97.75 | 92.25 | 84.75 | 83.5 | 79 | 67.5 | 66 | 64 | 57 | 50 | 41 | 34 | 23.5 | 12.5 | 0
|  |  | Ideal | 106.25 | 100.9375 | 95.625 | 90.3125 | 85 | 79.6875 | 74.375 | 69.0625 | 63.75 | 58.4375 | 53.125 | 47.8125 | 42.5 | 37.1875 | 31.875 | 26.5625 | 21.25 | 15.9375 | 10.625 | 5.3125 | 0