## GANTT CHART
Gantt Chart
| Project Start | 2025-03-31 |  |  | columns used to create the chart
CATEGORY | TASK | START | END | COLOR | Start | Blue | Red | Green | Brown | Orange | Purple
Planning | Define Team Roles and Responsibilities #1 | 2025-04-08 | 2025-04-08 | Blue | 2025-04-08 | 1 | 0 | 0 | 0 | 0 | 0
| Gantt Chart and Task Dependencies #2 | 2025-04-08 | 2025-04-08 | Blue | 2025-04-08 | 1 | 0 | 0 | 0 | 0 | 0
Documentation | Generate Sprint 1 Burndown Chart #3 | 2025-04-09 | 2025-04-10 | Blue | 2025-04-09 | 2 | 0 | 0 | 0 | 0 | 0
| SysML diagram for 15 FR. #4 | 2025-04-10 | 2025-04-15 | Blue | 2025-04-10 | 6 | 0 | 0 | 0 | 0 | 0
| Model Main Business Process (BPMN) #5 | 2025-04-12 | 2025-04-16 | Red | 2025-04-12 | 0 | 5 | 0 | 0 | 0 | 0
Back End | Implement Back-End Logic for Basic Features #8 | 2025-04-15 | 2025-04-22 | Red | 2025-04-15 | 0 | 8 | 0 | 0 | 0 | 0
Front End | Design Front-End UI #6 | 2025-04-16 | 2025-04-20 | Red | 2025-04-16 | 0 | 5 | 0 | 0 | 0 | 0
| Implement Front-End #7 | 2025-04-18 | 2025-04-23 | Red | 2025-04-18 | 0 | 6 | 0 | 0 | 0 | 0
Quality | Quality Check and Testing #9 | 2025-04-22 | 2025-04-27 | Green | 2025-04-22 | 0 | 0 | 6 | 0 | 0 | 0
Insert new rows above this one
| MILESTONE LABEL | DATE | Margin Bottom | Margin Top
| Start Coding | 2025-04-17 | 50% | 95%
| 1st Delivery | 2025-04-27 | 25% | 95%
| 2nd Delivery | 2025-05-31 | 10% | 95%
Formulas:
Start = IF(ISBLANK([START]),0,[START])

## BURNDOWN CHART
Burndown Chart
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
CATEGORY | TASK | START | END | ESTIMATE (Hours) | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | REMAINING WORK
Planning | Define Team Roles and Responsibilities #1 | 2025-04-08 | 2025-04-08 | 1 | [20 empty] | 1
| Gantt Chart and Task Dependencies #2 | 2025-04-08 | 2025-04-08 | 2 | [20 empty] | 2
Documentation | Generate Sprint 1 Burndown Chart #3 | 2025-04-09 | 2025-04-10 | 3 | [20 empty] | 2 | bar: 2025-04-08
| SysML diagram for 15 FR. #4 | 2025-04-10 | 2025-04-15 | 4 | [20 empty] | 4
| Model Main Business Process (BPMN) #5 | 2025-04-12 | 2025-04-16 | 5 | [20 empty] | 5
Back End | Implement Back-End Logic for Basic Features #8 | 2025-04-15 | 2025-04-22 | 6 | [20 empty] | 6
Front End | Design Front-End UI #6 | 2025-04-16 | 2025-04-20 | 7 | [20 empty] | 7
| Implement Front-End #7 | 2025-04-18 | 2025-04-23 | 8 | [20 empty] | 8
Quality | Quality Check and Testing #9 | 2025-04-22 | 2025-04-27 | 9 | [20 empty] | 9
|  |  | Total | 45 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44
|  |  | Remaining | 45 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44
|  |  | Ideal | 45 | 42.75 | 40.5 | 38.25 | 36 | 33.75 | 31.5 | 29.25 | 27 | 24.75 | 22.5 | 20.25 | 18 | 15.75 | 13.5 | 11.25 | 9 | 6.75 | 4.5 | 2.25 | 0
Tasks Assigned |  |  | TEAM MEMBERS | ESTIMATE (Hours) | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | REMAINING WORK
|  |  | Bernardo Carvalho | 9 | [20 empty] | 8 | bar: 2025-04-08
Bernardo Carvalho: #X (Z hours) and #Y (W hours) |  |  | Guilherme Santana | 9 | [20 empty] | 9
Estimate time for Bernardo should be Z+W hours |  |  | João Félix | 9 | [20 empty] | 8 | bar: 2025-04-11
|  |  | Luís Lamy | 9 | [20 empty] | 8 | bar: 2025-04-08
|  |  | Yaroslav Hayduk | 9 | [20 empty] | 9
|  |  | Total | 45 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42
|  |  | Remaining | 45 | 43 | 43 | 43 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
|  |  | Ideal | 45 | 42.75 | 40.5 | 38.25 | 36 | 33.75 | 31.5 | 29.25 | 27 | 24.75 | 22.5 | 20.25 | 18 | 15.75 | 13.5 | 11.25 | 9 | 6.75 | 4.5 | 2.25 | 0