## ProjectTimeline
Gannt Chart
| Project Start | 2025-03-31 |  |  | columns used to create the chart
CATEGORY | TASK | START | END | COLOR | Start | Blue | Red | Green | Brown | Orange | Purple
Planning | Define Team Roles and Responsibilities #1 | 2025-04-08 | 2025-04-08 | Blue | 2025-04-08 | 1 | 0 | 0 | 0 | 0 | 0
| Gantt Chart and Task Dependencies #2 | 2025-04-08 | 2025-04-08 | Blue | 2025-04-08 | 1 | 0 | 0 | 0 | 0 | 0
Documen tation | Generate Sprint 1 Burndown Chart #3 | 2025-04-09 | 2025-04-10 | Blue | 2025-04-09 | 2 | 0 | 0 | 0 | 0 | 0
| SysML diagram for 15 FR. #4 | 2025-04-10 | 2025-04-15 | Blue | 2025-04-10 | 6 | 0 | 0 | 0 | 0 | 0
| Model Main Business Process (BPMN) #5 | 2025-04-12 | 2025-04-16 | Red | 2025-04-12 | 0 | 5 | 0 | 0 | 0 | 0
Back End | Implement Back-End Logic for Basic Features #8 | 2025-04-15 | 2025-04-22 | Red | 2025-04-15 | 0 | 8 | 0 | 0 | 0 | 0
Front End | Design Front-End UI #6 | 2025-04-16 | 2025-04-20 | Red | 2025-04-16 | 0 | 5 | 0 | 0 | 0 | 0
| Implement Front-End #7 | 2025-04-18 | 2025-04-23 | Red | 2025-04-18 | 0 | 6 | 0 | 0 | 0 | 0
Qua lity | Quality Check and Testing #9 | 2025-04-22 | 2025-04-27 | Green | 2025-04-22 | 0 | 0 | 6 | 0 | 0 | 0
Insert new rows above this one
| MILESTONE LABEL | DATE | Margin Bottom | Margin Top
| Start Coding | 2025-04-17 | 50% | 95%
| 1st Delivery | 2025-04-27 | 25% | 95%
| 2nd Delivery | 2025-05-31 | 10% | 95%
Formulas:
Start = IF(ISBLANK([START]),0,[START])